## Project Plan
Project:
Task | Start Date | Duration (days)
Project Starts
Research and read notes | 2019-07-08 | 4
Decide on what techniques to use | 2019-07-12 | 2
Learn how to implement | 2019-07-14 | 7
Find patterns and segmentation | 2019-07-21 | 2
Implement text segmentation | 2019-07-23 | 2
Implement chosen technique to extract info | 2019-07-25 | 10
Decide what info to use based on content | 2019-08-04 | 7
Research about language generation | 2019-08-11 | 7 | Look up GPT-2
Implement language generation | 2019-08-18 | 21
Working version | 2019-09-08 | 5
Debugging and improving | 2019-09-13 | 10
Final version | 2019-09-23
Project Ends | 2019-09-23
Note that the tasks shown here are put in sequential order - realistically a number of these tasks can and should be run in parrallel, allowing you more time and better resource allocation.
Formulas:
Start Date = [Start Date, row above]+[Duration (days), row above]